JUST LOVE FOREST

Custom Event Management ERP

Implementation Roadmap

February 23 – March 23, 2026

Prepared by: Brandon James Abbott

Date: February 23, 2026 | Companion to PRD v3

# 1. Roadmap Overview

This roadmap reflects the architectural pivot from “bridge two systems” (PRD v2) to “single-system registration flow” (PRD v3). The timeline is organized in a Now / Next / Later format with four implementation phases spanning approximately four weeks.

## 1.1 Architecture Context

The previous roadmap (PRD v2) was organized around building a reconciliation engine between Acuity and Stripe. That approach required Acuity API access (a go/no-go risk), a matching engine, multiple webhook handlers, and six attendee states. The new approach eliminates all of that complexity by removing Acuity from the booking flow entirely.

New flow: Custom Registration Form → Stripe Checkout → PostgreSQL. One system, one database, atomic by design.

## 1.2 Capacity & Constraints

- Brandon is the sole developer, currently interviewing for roles and traveling intermittently.

- Effective capacity: approximately 15–20 hours/week of focused development time.

- March events are approaching — the current payment-first flow (Stripe → Acuity) is already live as a stopgap.

- Brian needs Stripe test-mode API keys before Phase 1 development can begin.

# 2. Now / Next / Later

## NOW — Phase 1: Foundation + Registration (Feb 23 – Mar 2)

The critical path. Delivers the single most important capability: attendees can register and pay in one flow.

| Item | Description | Status | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| Confirm architecture with Brian & Naveed | Present PRD v3 + analysis. Get buy-in on dropping Acuity from the booking path. | Not Started | Brandon | None — go/no-go gate |
| Set up dev environment | FastAPI project, PostgreSQL on Railway/Supabase, Stripe test mode, CI/CD pipeline. | Not Started | Brandon | Architecture confirmed; Stripe test keys from Brian |
| Database schema | Events, Attendees, Registrations tables (simplified from PRD v2 — no matching engine). | Not Started | Brandon | Dev environment |
| Build registration form | Custom intake form (Next.js) matching Acuity’s current fields + waiver. Hosted on Vercel. | Not Started | Brandon | DB schema; intake field list from Brian |
| Stripe Checkout integration | Create Checkout Sessions from form submissions; handle checkout.session.completed webhook. | Not Started | Brandon | Dev environment; Stripe test keys |
| PENDING_PAYMENT handling | Auto-expire logic + first reminder email for incomplete registrations. | Not Started | Brandon | Stripe integration |

Phase 1 Milestone: An attendee can register and pay in a single flow, with data in PostgreSQL. This alone solves the #1 problem.

## NEXT — Phase 2: Dashboard + Operator Tools (Mar 2 – Mar 9)

Gives Brian visibility. Replaces the spreadsheet reconciliation workflow.

| Item | Description | Status | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| Operator dashboard | Event overview, attendee list, payment status, accommodation/dietary breakdown, revenue. | Not Started | Brandon | Phase 1 complete |
| Event management UI | Brian can create/edit events, set pricing model, configure registration fields. | Not Started | Brandon | Phase 1 complete |
| Attendee search + filtering | Search by name/email, filter by status/event/accommodation type. | Not Started | Brandon | Dashboard |
| CSV export | Per-event export for offline/field use. | Not Started | Brandon | Dashboard |

Phase 2 Milestone: Brian can see all event data in one place. No more spreadsheet reconciliation.

## NEXT — Phase 3: Automation + Portal (Mar 9 – Mar 16)

Automates communications and enables co-host self-service.

| Item | Description | Status | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| Automated email reminders | Configurable reminders for PENDING_PAYMENT records (60-min default, 12-hr escalation). | Not Started | Brandon | Phase 1 |
| Co-creator portal | Read-only, event-scoped view with magic link authentication. | Not Started | Brandon | Phase 2 |
| Day-of SMS | Twilio integration for logistics notifications to COMPLETE attendees. | Not Started | Brandon | Phase 1; Twilio setup |
| Manual overrides | Mark as paid (cash/comp), add walk-ins, edit attendee data. | Not Started | Brandon | Phase 2 |

Phase 3 Milestone: Full MVP. Co-hosts are self-service. Reminders are automated.

## LATER — Phase 4: Hardening + Migration (Mar 16 – Mar 23)

Production readiness. Parallel testing, documentation, and domain migration.

| Item | Description | Status | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| Parallel testing | Run alongside current workflow for 1–2 live events. Compare outputs. | Not Started | Brandon + Brian | Phase 3 |
| Squarespace integration | Update event pages to link to custom registration form (URL swap). | Not Started | Brian | Phase 1 tested |
| SOP documentation | Operating procedures for Brian, Naveed, and co-hosts. | Not Started | Brandon | Phase 3 |
| Domain migration | Move from Vercel staging to justloveforest.com. | Not Started | Brandon + Brian | Parallel testing passed |

Phase 4 Milestone: Production-ready. Zapier decommissioned. Brian is operational.

# 3. Dependencies & Blocking Items

## 3.1 Critical Dependencies

| Dependency | Needed By | Owner | Status | Fallback |
| --- | --- | --- | --- | --- |
| Architecture approval (drop Acuity from booking) | Before any development | Brian + Naveed | Confirmed (verbal) | Option 2: hybrid sync to Acuity after payment |
| Stripe test-mode API keys | Phase 1 start | Brian | Not Yet Provided | Cannot proceed with Stripe integration without this |
| Acuity intake form field list | Phase 1 (registration form) | Brian | Not Yet Provided | Brandon reviews Acuity forms directly if Brian shares login |
| Squarespace event page structure | Phase 4 (URL swap) | Brian | Unknown | Brandon reviews site to assess integration approach |

## 3.2 Technical Dependencies

- Railway/Supabase account setup → blocks database deployment

- Twilio account + phone number → blocks Phase 3 SMS feature

- Domain DNS access (justloveforest.com) → blocks Phase 4 migration

- Resend/SendGrid account → blocks email reminders and confirmations

# 4. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Brandon’s availability (interviews + travel) | Medium | Medium | Front-load architecture decision this week. Phase 1 coding in focused bursts. Current flow is live as stopgap. |
| March event arrives before Phase 2 | Medium | Medium | Phase 1 alone solves the core registration problem. Dashboard can follow. Current Stripe → Acuity flow remains as backup. |
| Stripe API key not provided promptly | Low | High (blocking) | Escalate in next call. Can use Stripe test keys for initial sandbox work. |
| Scope creep beyond 4-week timeline | High | Medium | Strict MoSCoW prioritization. Defer all Should-Have items if timeline slips. Weekly check-ins to re-assess. |
| Squarespace integration more complex than expected | Low | Low | Worst case: use a standalone URL (not embedded in Squarespace) until integration is sorted. |
| Webhook delivery failures in production | Medium | High | Idempotent handlers; Stripe auto-retry (72h); daily reconciliation cron as safety net. |

# 5. Roadmap Changes from PRD v2

This section documents what changed and why, for stakeholder reference.

| Area | PRD v2 Roadmap | PRD v3 Roadmap | Impact |
| --- | --- | --- | --- |
| Sprint 0 (Discovery) | Validate Acuity API access (go/no-go gate) | Eliminated — no Acuity dependency | Removed biggest project risk |
| Sprint 1 (Core Integration) | Build Acuity + Stripe webhook handlers + matching engine (20–25 hrs) | Build registration form + Stripe Checkout (15–20 hrs) | Simpler, less code, fewer bugs |
| Sprint 2 (Dashboard) | Dashboard + reconciliation views + NEEDS_REVIEW queue (20–25 hrs) | Dashboard + event management (12–18 hrs) | No exception queue needed |
| Sprint 3 (Portal + SMS) | Co-creator portal + SMS + hardening (15–20 hrs) | Split into Phase 3 (automation) + Phase 4 (hardening) (18–27 hrs) | More time for testing and docs |
| Total estimated effort | 63–82 hours | 45–60 hours | 25–30% reduction |
| Timeline | 4 weeks (Feb 3–28) | 4 weeks (Feb 23–Mar 23) | Shifted but same duration |

# 6. Immediate Next Steps

## 6.1 For Brandon (This Week)

- Send PRD v3 + meeting analysis to Brian and Naveed for review.

- Confirm architecture decision in next call (or async via document review).

- Set up dev environment: FastAPI project skeleton, PostgreSQL on Railway, Stripe test mode.

- Begin database schema implementation once Stripe test keys are received.

- Draft registration form wireframe based on Acuity’s current intake fields.

## 6.2 For Brian (This Week)

- Review PRD v3 and confirm or push back on dropping Acuity from the booking flow.

- Provide Stripe test-mode API keys to Brandon.

- Share current Acuity intake form fields (screenshot or list).

- Confirm first March event date (hard deadline for stopgap vs. new system).

- Share how events are listed on justloveforest.com (Squarespace page structure).

## 6.3 For Naveed

- Review PRD v3 architecture and provide feedback.

- Confirm any additional operational requirements not captured in the PRD.

End of Roadmap — Companion to PRD v3.0